## Slide 1: MS PROJECT SCHEDULE USING AGILE TECHNIQUES
The schedule is set to run from April 1st to Sept 28, a total of 181 days.
The task that will start will be project initialization, methodology selection, then planning phase, Project Charter Development, AI Tool Development, Execution and Closure and reporting.
On April 1, the project initialization will begin with media announcement on April 1. That will be done after meeting with Helen, Murat, and TPZ to discuss project details and confirming the project lead. The other tasks that will be carried out under the initialization phase on day 1 will include;
Choosing the methodology in this case, an agile approach, which will allow the team to adapt to changes and iterate the product throughout the project, providing continuous delivery and feedback from key stakeholders because the requirements are not defined at this point in time.
Discussing missing buy-in from Business Unit Leaders
Clarifying the importance of timing for AI 2025 functionality and personnel cost savings.
Reviewing and adjusting the fee structure.

## Slide 2: PLANNING PHASE
This phase will have the following tasks which will be carried out within 1 week
A project Pre-Mortem as requested by Helen.
Provide initial thoughts on the contract type (Fixed Fee, T&M, etc.) and reasons.
Identify potential KPIs for the project.
  Satisfaction rate- Ask AI technology and dashboard users to complete a short survey to measure satisfaction and effectiveness with the project at set dates to identify potential problems
  Adoption Rate (%) - Measure what percentage of employees in all business units are using the new technology and dashboard at set dates to measure rollout process
  Cost Reduction (%) - Measure company costs before, during and after project rollout to measure the effect of streamlining processes and reducing redundancies within the company
Submit the project schedule to Liz for approval from stakeholders.

## Slide 3: Project charter development
Develop a Project Charter outlining the project's goals, scope, stakeholders, and the chosen project management technique.
Identify and analyze key stakeholders, understanding their goals and motivations.
Review and approval of the MS Project schedule by key stakeholders. This will take 1 week
Execute the project based on the approved schedule.

## Slide 4: AI 2025 DEVELOPMENT
Develop the global AI tool for forecasting consumer demand by consolidating tools from the two business units. This will be assigned to TPZ
Conduct requirements gathering sessions with stakeholders from both business units.
Collaborate with TPZ on the design and development of the AI tool.
Implement features for accurate sales forecasting and cost reduction.
Establish regular review sessions with key stakeholders to gather feedback on tool development progress.
Use the key performance indicators (KPIs) to executive decision-making.
Work with a user experience (UX) designer to create a visually appealing and intuitive dashboard interface.
Conduct usability testing sessions with executives to gather feedback and make necessary adjustments.
Ensure seamless integration of the dashboard with the AI tool for real-time data updates.

## Slide 5: EXECUTION
The tasks here will be done under execution.
Plan and execute initiatives for cost reduction, including personnel layoffs, while minimizing disruption to operations.
Collaborate with HR and finance teams to analyze current labor costs and identify areas for reduction.
Develop a communication plan for announcing layoffs and managing employee concerns.
Implement training programs to ensure a smooth transition from existing forecasting processes to the new AI tool.
Monitor and report on the financial impact of cost reduction initiatives.

## Slide 6: Closure and reporting
The tasks here include; Engage with key stakeholders to secure buy-in and ensure alignment with project goals.
Conduct stakeholder analysis to identify individuals and groups affected by the project.
Schedule regular communication sessions with business unit leaders to address concerns and gather support.
Develop a comprehensive stakeholder engagement plan, including communication channels and frequency.
Establish a feedback loop to capture stakeholder input and adjust project plans accordingly.
Key Milestones include the following;
Milestone 1: Project initiation and confirmation of the project lead.
Milestone 2: Proposal submission and approval.
Milestone 3: Project management technique selection.
Milestone 4: Approval of the Project Charter and MS Project schedule.
Milestone 5: Full-time role initiation and Project Coordinator onboarding.